## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Mushrooms By the Sea: e-commerce website
Team Agile |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2022-02-14 |  |  |  |  | February | [20 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2022-02-14 to 2022-04-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-02-14 to 2022-04-10
Iteration 1
Stakeholder Register | On Track | All | 100% | 2022-02-21 | 2
Persona 1 | On Track | Russell Ruru | 100% | 2022-02-28 | 2
Persona 2 | On Track | Lilia Karl | 100% | 2022-02-28 | 2
Persona 3 | On Track | Lilia Karl | 100% | 2022-02-28 | 2
Persona 4 | On Track | Cole Yuile | 100% | 2022-02-28 | 2
Persona Testing | On Track | All | 100% | 2022-03-07 | 1
Markdown Stakeholder Register | On Track | Cole Yuile | 100% | 2022-02-28 | 1
Markdown Personas | On Track | Russell Ruru | 100% | 2022-03-14 | 2
Markdown Group Meeting Reports | On Track | Lilia Karl | 100% | 2022-02-28 | 2
Iteration 1 Report | Milestone | All | 100% | 2022-03-14 | 2 | bar: 2022-03-14 to 2022-03-15
Iteration 1 Complete | Goal | All | 100% | 2022-03-16 | 2 | 2022-03-16: 2; 2022-03-17: 2
Iteration 2
Stakeholder Register | On Track | All | 100% | 2022-02-21 | 1
Markdown Group Meeting Report | On Track | Cole Yuile | 100% | 2022-03-23 | 1
Markdown Progress Report | On Track | Cole Yuile | 100% | 2022-04-12 | 2
Iteration 1: Resource Needs Report | On Track | Lilia Karl | 100% | 2022-04-07 | 1
Resource Needs | On Track |  | 100% | 2022-05-02 | 0
Iteration 1: Gant Chart | On Track | Lilia Karl | 100% | 2022-04-04 | 2
Iteration 2: Gant Chart | On Track | Russell Ruru | 100% | 2022-04-11 | 1
Markdown documents to GitHub | On Track | All | 100% | 2022-04-13 | 2
Iteration 2 Report | Milestone | Russell Ruru | 100% | 2022-04-14 | 2
Iteration 2 Complete | Goal | All | 100% | 2022-04-28 | 2
Iteration 3
Markdown Group Meeting Report | On Track | Cole Yuile | 75% | 2022-05-02 | 0
Markdown documents to GitHub | On Track | All | 75% | 2022-05-02 | 0
Risk Register | On Track |  | 75% | 2022-05-02 | 0
Github | Med Risk | All | 75% | 2022-05-02 | 0
Iteration 3 Gantt Chart | On Track | Cole Yuile | 100% | 2022-05-02 | 0
Iteration 3 Report | Milestone | Cole Yuile | 100% | 2022-05-02 | 2
User Acceptance Test Results | Med Risk | All | 75% | 2022-05-02 | 2
Create static website | Med Risk | All | 100% | 2022-05-02 | 2
Iteration 3 Complete | Goal | All | 75% | 2022-04-28 | 2
Final Handover
Check Group Name and Group Members | Med Risk | Russell Ruru |  | 2022-05-23 | 2
Check link to Group's GitHub repository | Med Risk | Cole Yuile |  | 2022-05-25 | 2
Check link to Group's readme.md documentation | Med Risk | Cole Yuile |  | 2022-05-25 | 2
Download .ZIP file | Low Risk | All |  | 2022-05-23
Upload .ZIP file to repository | Low Risk | All |  | 2022-05-23
Check readme.md file is complete | On Track | Lilia Karl | 25% | 2022-05-25 | 2
Final Handover Upload | Goal | All |  | 2022-05-29 | 2

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-30 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2022-05-31 to 2022-07-25
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-30 | 3 | T: 2; W: 2
Task 2 | Milestone |  |  | 2022-06-04 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2022-05-27 | 10
Task 4 | Milestone |  |  | 2022-06-19 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2022-06-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-06-05 | 13
Task 2 | On Track |  | 50% | 2022-06-07 | 9
Task 3 | Low Risk |  | 33% | 2022-06-12 | 11
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: T
Task 5 |  |  |  | 2022-06-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-14 | 4
Task 2 | Med Risk |  |  | 2022-06-17 | 14
Task 3 | On Track |  |  | 2022-07-02 | 6
Task 4 | Goal |  |  | 2022-07-06 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2022-06-05 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-09 | 15
Task 2 |  |  |  | 2022-07-23 | 5
Task 3 | Milestone |  |  | 2022-09-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-30 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2022-06-04 to 2022-07-29
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-06-04 to 2022-07-29
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-30 | 3
Task 2 | Milestone |  |  | 2022-06-04 | 1 | bar: 2022-06-04
Task 3 | Low Risk |  | 50% | 2022-05-27 | 10
Task 4 | Milestone |  |  | 2022-06-19 | 1 | bar: 2022-06-19
Task 5 | Med Risk |  | 10% | 2022-06-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-06-05 | 13
Task 2 | On Track |  | 50% | 2022-06-07 | 9
Task 3 | Low Risk |  | 33% | 2022-06-12 | 11
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: 2022-06-14
Task 5 |  |  |  | 2022-06-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-14 | 4
Task 2 | Med Risk |  |  | 2022-06-17 | 14
Task 3 | On Track |  |  | 2022-07-02 | 6
Task 4 | Goal |  |  | 2022-07-06 | 3 | 2022-07-06: 2; 2022-07-07: 2; 2022-07-08: 2
Task 5 | Low Risk |  |  | 2022-06-05 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-09 | 15
Task 2 |  |  |  | 2022-07-23 | 5
Task 3 | Milestone |  |  | 2022-09-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one